## Summary
Project Name/ Number | Bhumae Wellness
Test Case Authorizing Date | 2026-10-09 | Application | Bhumae Wellness e-commerce website (bhumaewellness.com) | Authorizing Effort | 8 hrs
|  |  |  | Execution Effort | 22.5 hrs
Plan Author | Kuldeep Tiru
Test Execution Date | 10 to 13 Oct | Version | Version 1 | Environment | Production (live site)
|  |  |  | Actual Time | 30 hrs
Test Executed By | Kuldeep Tiru
Test Status | Executed, pending review
Scope | Entire website: storefront (home, collection, product, bag, checkout, PIN code, discounts, COD), emails, order tracking, account, policy and contact pages, admin (orders, invoice, products, discounts, content), plus responsive, compatibility, accessibility, performance and basic security checks. Includes the client plan (35 checks S1-S14, T1-T6, A1-A11, D1-D4) and added cases.
Test Purpose or Objective | Confirm the site is ready for launch on Oct 12, 2026. Complete execution by Oct 11, 2026 and report defects with device, browser, URL, steps, actual vs expected and evidence.
Set Up Requirements or Considerations | Android phone (Chrome), iPhone (Safari), desktop (Chrome or Edge, Firefox), Mac Safari if available. Own name, mobile and email on test orders. Admin password shared separately.
Notes or Special Instructions | Every order is real in the system. Cancel each test order in admin and note its BHU reference. Do NOT click Ship via courier partner. Restore any price, stock or photo that is edited. Create discount codes (ADM_010) before DISC_001.
Database Changes | Test data created during execution was cleaned up after testing.
Hardware or Network | Android, iPhone, desktop and Mac browsers; Wi-Fi and mobile data; Chrome DevTools and Lighthouse.
Items not included in test | Online payment (payment gateway), customer sign-in by SMS, Ship via courier partner, shipping labels, live courier tracking (client excluded). Load testing, penetration testing, database access.
Assumptions | Business rules agreed with the client at the start: free-shipping threshold, quantity cap, COD limit and GST-inclusive pricing.
Work Sheets in Test plan | All the projects should have Functional testing, Regression Testing work sheets. New work sheets can be added in case of the testing multiple modules/applications/roles/permissions
Defect List | All the defects should be tracked in the test plan.

## Execution Plan
Phase | When | Test Case Ids | Dependency and notes | Est. hours
0. Setup | Oct 10 | ADM_001, ADM_010, PIN_012 | Get admin password and devices ready. Record every product price, MRP, stock and photo before editing anything (baseline stock 24, 24, 25, 25, 25). Create discount codes first (needed by DISC_001, DISC_002, DISC_003). Prepare a folder for screenshots. | 0.5
1. Storefront on desktop | Oct 10 | HOME_001, HOME_002, COLL_001, COLL_002, PDP_001, PDP_002, BAG_001, BAG_002, BAG_003, BAG_004, BAG_007, CHK_001, CHK_002, CHK_003, PIN_001, PIN_002, PIN_003, PAY_001, PAY_002, DISC_001, DISC_002, DISC_003, DISC_004, COLL_003, COLL_004, PDP_006, PDP_007, PDP_008, PDP_009, BAG_010, BAG_011, PAY_003, NAV_006, NAV_007, NAV_008 | No orders placed yet. Use PIN data from the client table. | 5.5
2. Order, emails, tracking, invoice | Oct 10 | ORD_001 (also place one order to 110001), CHK_010, ORD_002, ORD_003, CHK_004, EML_001, EML_002, EML_003, TRK_001, TRK_002, TRK_003, TRK_004, ADM_002, ADM_003, ADM_017, ADM_004, then ADM_005 | Needs the S11 order. Cancel (ADM_005) only after invoice, tracking and email checks are finished. Write BHU references in Notes. | 3.5
3. Admin and stock | Oct 10 late or Oct 11 early | ADM_006, STK_001, ORD_004, BAG_008, ADM_007, ADM_008, ADM_009, ADM_013, ADM_014, ADM_015, ADM_016, ADM_018, ADM_012, SEC_001, ADM_019, ADM_020, ADM_021, ADM_022, ADM_023, ADM_025, ADM_026, SEC_002, ADM_011, ACC_001, POL_001, POL_002 | Restore price, stock and photos after each check. Delete test products at the end. Never click Ship via courier partner. Change payment settings only in a quiet period and restore. | 5
4. Devices | Oct 11 AM | DEV_001, DEV_002, DEV_003, DEV_004, CHK_007, NAV_002, PDP_004, UI_001 | Each device run places a real order. Cancel it and note the BHU reference. | 3
5. Remaining and non-functional | Oct 11 (stretch) | NAV_001, NAV_003, NAV_004, NAV_005, HOME_003, PDP_003, PDP_005, BAG_005, BAG_006, BAG_009, CHK_005, CHK_006, CHK_008, CHK_009, ORD_005, UI_002, UI_003, UI_004, UI_005, UI_006, UI_007, UI_008, UI_009, EXP_001 | Stretch phase. If time runs short, run High priority cases only and report the rest as Not Executed. Exploratory session is time-boxed to 60 minutes per device. | 3.5
6. Retest and wrap-up | Oct 11 PM | Regression sheet (High priority cases), all Failed and Blocked cases | Retest fixes. Cancel all test orders, restore data, update Defects sheet and send the summary report before the deadline. | 1.5
Total |  |  |  | 22.5
Prefix TC_BW_ is omitted in Case Ids for brevity (for example ADM_001 means TC_BW_ADM_001).

## Coverage
Test Type | Total | Pass | Fail | Blocked | Not Executed | % Executed
Accessibility | 1 | 1 | 0 | 0 | 0 | 100%
Admin | 16 | 14 | 0 | 2 | 0 | 100%
Boundary | 6 | 5 | 0 | 1 | 0 | 100%
Compatibility | 5 | 3 | 0 | 1 | 0 | 80%
Content | 6 | 6 | 0 | 0 | 0 | 100%
Data Integrity | 13 | 12 | 1 | 0 | 0 | 100%
Email | 4 | 4 | 0 | 0 | 0 | 100%
End-to-End | 1 | 1 | 0 | 0 | 0 | 100%
Error Handling | 4 | 3 | 1 | 0 | 0 | 100%
Exploratory | 1 | 1 | 0 | 0 | 0 | 100%
Functional | 22 | 19 | 1 | 2 | 0 | 100%
Integration | 2 | 1 | 1 | 0 | 0 | 100%
Navigation | 4 | 4 | 0 | 0 | 0 | 100%
Negative | 7 | 7 | 0 | 0 | 0 | 100%
Performance | 1 | 0 | 0 | 0 | 0 | 0%
Responsive | 1 | 0 | 1 | 0 | 0 | 100%
SEO | 2 | 1 | 0 | 1 | 0 | 100%
Security | 6 | 3 | 2 | 1 | 0 | 100%
State and Session | 3 | 3 | 0 | 0 | 0 | 100%
UI and Visual | 2 | 2 | 0 | 0 | 0 | 100%
Usability | 1 | 1 | 0 | 0 | 0 | 100%
Validation | 5 | 3 | 2 | 0 | 0 | 100%
Total | 113 | 94 | 9 | 8 | 0 | 98.23%
Priority summary
Priority | Total | Pass | Fail | Blocked | Not Executed | % Executed
High | 61 | 50 | 8 | 3 | 0 | 100%
Medium | 44 | 38 | 1 | 4 | 0 | 97.73%
Low | 8 | 6 | 0 | 1 | 0 | 87.5%
Not covered in this round
Area | Reason | Suggested owner
Load and stress testing | Needs tooling (k6, JMeter) and a staging target, not manual | Developer
Penetration or vulnerability scan | Only basic manual security checks are done (SEC cases) | Developer or security vendor
Online payment (UPI, cards) | Switched off until payment gateway approves the account (client) | Retest when live
Customer sign-in by SMS | Waiting on SMS registration (client) | Retest when live
Ship via courier partner, labels, live courier tracking | Books a real courier and charges the wallet (client) | Developer
Database and API level checks | No database access; network tab observation only | Developer
Older OS and browser versions, device farm | Only the available devices are tested | Optional
Email clients beyond Gmail and one more | Partial coverage in EML_003 | Optional
Legal and tax compliance review | Invoice maths is checked; legal wording and GSTIN rules are for the client | Client or CA

## Functional Testing
Test Case Id | Requirement # | Test Scenario | Test Cases | Pre-condition | Test Steps | Step Description | Test data | Expected Results | Actual Results | Priority | Status | Test Type | Run On
TC_BW_HOME_001 | S1 | Home page | Verify home page, product carousel and links | Fresh browser session | Step 01 | Open the home page | https://bhumaewellness.com | Page loads with no errors; carousel moves; links open the right pages |  | High | Pass | Functional | Both
[5 empty] | Step 02 | Move the product carousel
[5 empty] | Step 03 | Click a few links
TC_BW_COLL_001 | S2 | Collection page | Verify category tabs and search | Collection page reachable | Step 01 | Open /collection | Search: rose | Each tab shows only its products and the tab counts are correct; search finds Rose Petal Powder; sorting reorders the list |  | High | Blocked | Functional | Both
[5 empty] | Step 02 | Click each category tab and compare the count in brackets with the products shown
[5 empty] | Step 03 | Search 'rose'
[5 empty] | Step 04 | Use the Sort products dropdown
TC_BW_PDP_001 | S3 | Product page | Verify product page photos, price, reviews and WhatsApp | Any product | Step 01 | Open /products/beetroot | Beetroot Powder, price ₹399 | Photos switch; price and MRP shown; Reviews says 'No reviews yet'; WhatsApp opens; every tab shows its own content |  | High | Pass | Functional | Both
[5 empty] | Step 02 | Click each gallery photo (4 thumbnails)
[5 empty] | Step 03 | Open each tab: The Ritual & Directions, Ingredients & Provenance, Pouch Specifications, Reviews (0)
[5 empty] | Step 04 | Click Consult on WhatsApp with Practitioner
TC_BW_BAG_001 | S4 | Bag | Verify bag add, quantity change, remove and free-delivery note | Empty bag | Step 01 | Add Beetroot (₹399) and Orange Peel (₹349) to the bag | Beetroot 399, Orange Peel 349 | Bag opens as 'The Bag (n)'; subtotal, shipping and total update correctly; the 'Add ₹X more for FREE shipping' note and progress bar update (₹399 alone shows 'Add ₹200 more') |  | High | Pass | Functional | Both
[5 empty] | Step 02 | Open the bag and change quantities
[5 empty] | Step 03 | Remove one product
[5 empty] | Step 04 | Compare subtotal, shipping and total with a manual calculation
TC_BW_BAG_002 | S5 | Bag | Verify quantity limit of 10 | 1 product in bag | Step 01 | Increase one product quantity to 10 | 10, 11 | Quantity stops at 10 |  | High | Pass | Boundary | Both
[5 empty] | Step 02 | Try to set 11 (button and typed)
TC_BW_CHK_001 | S6 | Checkout form | Verify empty and invalid checkout fields | Item in bag, on checkout | Step 01 | Click Place Order with empty fields | Phone 12345, email abc@ | A clear error under each required field (email, mobile, address, city, state, PIN; confirm whether Full name is required, its label shows no asterisk); no order placed |  | High | Pass | Validation | Both
[5 empty] | Step 02 | Enter phone 12345 and a wrong email
[5 empty] | Step 03 | Click Place Order
TC_BW_PIN_001 | S7 | PIN code | Verify deliverable PIN 202002 | On checkout | Step 01 | Enter PIN 202002 with city empty | 202002 | 'Delivery available to Aligarh'; city fills in by itself if empty |  | High | Pass | Functional | Both
[5 empty] | Step 02 | Observe message and city field
TC_BW_PIN_002 | S8 | PIN code | Verify non-served PIN 744101 blocks order | Valid details filled | Step 01 | Enter PIN 744101 | 744101 (Port Blair) | Message that the courier does not deliver there yet; order not placed |  | High | Pass | Negative | Both
[5 empty] | Step 02 | Read the message
[5 empty] | Step 03 | Try to place the order
TC_BW_PIN_003 | S9 | PIN code | Verify non-real PIN 999999 blocks order | Valid details filled | Step 01 | Enter PIN 999999 | 999999 | '999999 is not a valid PIN code'; order not placed |  | High | Pass | Negative | Both
[5 empty] | Step 02 | Read the message
[5 empty] | Step 03 | Try to place the order
TC_BW_PAY_001 | S10 | Payment | Verify payment options display | On checkout | Step 01 | Look at the payment section | UPI and card options | Online payment (payment gateway, UPI, cards) is greyed out with 'Opening soon'; Cash on Delivery (Additional ₹30 fee) is selected |  | High | Pass | Functional | Both
[5 empty] | Step 02 | Try clicking the online payment option
TC_BW_ORD_001 | S11 | Order | Place a Cash on Delivery order end to end | Real name, mobile and email ready; PIN 202002 | Step 01 | Add a product | Beetroot x1, PIN 202002. Expect subtotal 399, shipping 49, COD fee 30, total 478; button reads PLACE CASH ON DELIVERY ORDER (₹478) | Confirmation page with an order reference (BHU-...); bag empties; totals match checkout (₹478) |  | High | Pass | End-to-End | Both
[5 empty] | Step 02 | Fill checkout with real details
[5 empty] | Step 03 | Select Cash on Delivery
[5 empty] | Step 04 | Place the order
[5 empty] | Step 05 | Note the BHU reference
TC_BW_DISC_001 | S12 | Discount codes | Verify discount codes apply, fail and remove (after A10) | Codes created in A10; use the Discount code box and Apply button in the checkout order summary | Step 01 | Apply a valid code | Codes from A10 | Discount line appears and applies to the products total only (shipping and the COD fee are never discounted); wrong code says 'not valid'; minimum-order message shows; Remove clears it |  | High | Pass | Functional | Both
[5 empty] | Step 02 | Apply a wrong code
[5 empty] | Step 03 | Apply the minimum-order code on a small bag
[5 empty] | Step 04 | Click Remove
TC_BW_PAY_002 | S13 | Payment | Verify COD limit above ₹5,000 | Bag builder | Step 01 | Add products until the bag exceeds ₹5,000 | Rose Petal x10 (₹4,990, check whether the ₹30 fee tips it over ₹5,000), then add Kaolin x1 (₹5,289) | Cash on Delivery shows 'Not available above ₹5,000' once the limit is crossed (expected until online payment opens); note which amount (subtotal or total with fee) is compared |  | High | Pass | Boundary | Both
[5 empty] | Step 02 | Open the payment section
TC_BW_STK_001 | S14 | Stock | Verify out of stock display | Admin access | Step 01 | In admin set a product's stock to 0 | Stock 0 then restore | Shop shows 'Currently out of stock' and no Add to bag |  | High | Pass | Functional | Desktop
[5 empty] | Step 02 | View it on the shop
[5 empty] | Step 03 | Put the stock back
TC_BW_EML_001 | T1 | Email | Verify order confirmation email | Order placed in S11 | Step 01 | Check the inbox of the email used | Own email | Arrives within a few minutes, in the inbox (not spam), from orders@bhumaewellness.com, with items, total, address and a Track your order link |  | High | Pass | Email | Both
[5 empty] | Step 02 | Check spam folder
[5 empty] | Step 03 | Verify sender, items, total, address and tracking link
TC_BW_EML_002 | T2 | Email | Verify store alert email | Order placed in S11 | Step 01 | Ask the team to check care@bhumaewellness.com | care@bhumaewellness.com | A 'New order' alert with the customer's details arrives |  | High | Pass | Email | Desktop
[5 empty] | Step 02 | Compare the details with the order
TC_BW_TRK_001 | T3 | Order tracking | Verify tracking by order reference | Order from S11 | Step 01 | Click Track your order in the email | BHU reference | Shows status, items and total; shows only name and city, never the full address or phone |  | High | Pass | Functional | Both
[5 empty] | Step 02 | Open Track Order page and enter the reference
[5 empty] | Step 03 | Check what is shown
TC_BW_TRK_002 | T4 | Order tracking | Verify tracking by mobile number | Order from S11 | Step 01 | Open Track Order page | Own mobile number | Lists the orders placed with that number |  | High | Pass | Functional | Both
[5 empty] | Step 02 | Enter your mobile number
[5 empty] | Step 03 | Review the list
TC_BW_ACC_001 | T5 | Account | Verify Account page | None | Step 01 | Open Account | N/A | Says sign-in is being set up and offers a Track an Order button that works |  | Low | Pass | Functional | Both
[5 empty] | Step 02 | Read the message
[5 empty] | Step 03 | Click Track an Order
TC_BW_POL_001 | T6 | Policy and contact | Verify policy and contact pages | Footer visible | Step 01 | Open Privacy, Terms, Refund and Shipping from the footer | 4 policies + Contact | Every page opens (Privacy policy, Terms & conditions, Refunds & cancellations, Shipping, Customer Account & Orders, WhatsApp Concierge); contact links open correctly |  | High | Pass | Navigation | Both
[5 empty] | Step 02 | Open Contact
[5 empty] | Step 03 | Click WhatsApp and email links
TC_BW_ADM_001 | A1 | Admin login | Verify sign in and sign out | Admin URL and password | Step 01 | Sign in with a wrong password | Wrong, then correct password | Wrong password: 'Incorrect password'; right one opens the dashboard; Sign Out returns to the sign-in screen |  | High | Pass | Admin | Desktop
[5 empty] | Step 02 | Sign in with the right password
[5 empty] | Step 03 | Click Sign Out
TC_BW_ADM_002 | A2 | Admin orders | Verify orders list | Order from S11 | Step 01 | Open Orders | BHU reference | Your S11 order shows with customer, address, items, total and status PENDING_COD |  | High | Pass | Admin | Desktop
[5 empty] | Step 02 | Find the S11 order
[5 empty] | Step 03 | Compare the details
TC_BW_ADM_003 | A3 | Admin invoice | Verify tax invoice (Aligarh and Delhi) | Own orders to 202002 and 110001. The existing Delhi COD order from another tester can also be used for the IGST check if the client agrees | Step 01 | Click Invoice on the COD order | 202002 and 110001 | Numbered BHU/26-27/...; a GSTIN warning shows (expected until added); Aligarh order shows CGST + SGST, Delhi order shows IGST; prints as one clean A4 page |  | High | Pass | Admin | Desktop
[5 empty] | Step 02 | Repeat for the Delhi order
[5 empty] | Step 03 | Click Print / Save PDF
TC_BW_ADM_004 | A4 | Admin emails | Verify Resend emails | Order exists | Step 01 | Click Resend emails on the order | Own order | Confirmation and store alert arrive again |  | Medium | Pass | Email | Desktop
[5 empty] | Step 02 | Check both inboxes
TC_BW_ADM_005 | A5 | Admin order status | Verify cancelling an order restores stock | Order of your own exists; run after A3, A4, T3, T4. The 2 existing orders belong to another tester, do not cancel or edit them | Step 01 | Note the product's stock | Own order | Status shows CANCELLED; the product's stock goes back up on the shop |  | High | Pass | Admin | Desktop
[5 empty] | Step 02 | Set Manual Status to Cancelled
[5 empty] | Step 03 | Check the shop stock
TC_BW_ADM_006 | A6 | Admin products | Verify editing price, MRP and stock | Admin access | Step 01 | Change a product's price, MRP and stock | Record originals first | Shop and product page show the new values, then the original ones |  | High | Pass | Admin | Desktop
[5 empty] | Step 02 | Check the shop and product page after refresh
[5 empty] | Step 03 | Change them back
TC_BW_ADM_007 | A7 | Admin products | Verify adding a product with photos | Photo file ready | Step 01 | Add New Product with name, price, stock, category | Test product (delete later) | Appears on Collection; its page opens with the photo, and the browser tab shows '<name> ¦ Bhumae Wellness' |  | High | Pass | Admin | Desktop
[5 empty] | Step 02 | Upload a front photo from phone or computer
[5 empty] | Step 03 | Save
[5 empty] | Step 04 | Check Collection and the product page
TC_BW_ADM_008 | A8 | Admin products | Verify gallery photos upload and removal | Product from A7 | Step 01 | Upload Gallery Photos (several) | 3 photos | All photos show on the product page; the removed one disappears |  | Medium | Pass | Admin | Desktop
[5 empty] | Step 02 | Save
[5 empty] | Step 03 | Remove one
[5 empty] | Step 04 | Save
[5 empty] | Step 05 | Check the product page
TC_BW_ADM_009 | A9 | Admin products | Verify deleting a product | Product from A7 | Step 01 | Delete the product | Product from A7 | Gone from Collection; its old link shows a not-found page |  | Medium | Pass | Admin | Desktop
[5 empty] | Step 02 | Check Collection
[5 empty] | Step 03 | Open its old link
TC_BW_ADM_010 | A10 | Admin discounts | Verify discount code management (run before S12) | Admin access | Step 01 | Open the Discount Codes tab (it shows 0 codes now) | 4 codes, add a Note to each | Codes list with the right status; Customers can use no code until one exists; expired and paused codes are refused at checkout; the private Note never appears on the storefront |  | High | Pass | Admin | Desktop
[5 empty] | Step 02 | Create a 10% code (Code, Type Percentage off, Percent off)
[5 empty] | Step 03 | Create a ₹100 off code with ₹700 minimum order
[5 empty] | Step 04 | Create a code whose Last day valid (dd-mm-yyyy) has passed
[5 empty] | Step 05 | Pause one
[5 empty] | Step 06 | Delete one
TC_BW_ADM_011 | A11 | Admin content | Verify Video & Reels tab | Admin access | Step 01 | Open Video & Reels | N/A | Shows the one BHUMAE Instagram post and no testimonials (cards: Customer video testimonials 0, Instagram reels and clips 1, Active motion proof assets 1) |  | Low | Pass | Admin | Desktop
[5 empty] | Step 02 | Compare with the storefront
TC_BW_DEV_001 | D1 | Device: Android | Run S1 to S11 on Android Chrome | Android phone | Step 01 | Run S1 to S11 | Android, Chrome | Text readable without zooming; buttons easy to tap; no sideways scrolling; checkout fits the screen |  | High | Blocked | Compatibility | Mobile
[5 empty] | Step 02 | Check readability, tap targets, sideways scroll and checkout fit
TC_BW_DEV_002 | D2 | Device: iPhone | Run S1 to S11 on iPhone Safari | iPhone | Step 01 | Run S1 to S11 | iPhone, Safari | Same as D1 |  | High | Pass | Compatibility | Mobile
[5 empty] | Step 02 | Check readability, tap targets, sideways scroll and checkout fit
TC_BW_DEV_003 | D3 | Device: Desktop | Run S1 to S11 and A1 to A11 on desktop Chrome or Edge | Desktop | Step 01 | Run S1 to S11 | Chrome or Edge | Everything works; admin tables readable |  | High | Pass | Compatibility | Desktop
[5 empty] | Step 02 | Run A1 to A11
[5 empty] | Step 03 | Check admin tables
TC_BW_DEV_004 | D4 | Device: Mac | Run S1 to S11 on Mac Safari (if available) | Mac available | Step 01 | Run S1 to S11 | macOS, Safari | Same as D3 |  | Low | N/A | Compatibility | Desktop
TC_BW_HOME_002 | Added | Home page | Verify hero, trust strip, section CTAs and the video | Home page loaded | Step 01 | Click the hero CTAs | Home page | Every CTA opens the intended page; no dead or # links; video controls work |  | High | Pass | Functional | Both
[5 empty] | Step 02 | Read the 4 trust items under the hero
[5 empty] | Step 03 | Click CTAs in each section
[5 empty] | Step 04 | Play, pause and mute the video
TC_BW_HOME_003 | Added | Content | Verify spelling, copy and consistency across all pages | Client copy available | Step 01 | Read every page | All pages | No typos, placeholder or lorem text; brand name consistent; values match everywhere |  | Medium | Pass | Content | Both
[5 empty] | Step 02 | Check brand name spelling (Bhumae vs 'bhumee' on the Collection heading)
[5 empty] | Step 03 | Compare prices, pack sizes and claims between card, product page, bag and email
[5 empty] | Step 04 | Check the ₹symbol
TC_BW_NAV_001 | Added | Navigation | Verify header menu, logo and sticky behaviour | Desktop | Step 01 | Click each header link: Store & Catalog, The Ritual, Our Story, Questions, Track Order, Contact | All header items | Each link opens the right page; logo returns home; header does not overlap content; Bag shows the item count |  | High | Pass | Navigation | Desktop
[5 empty] | Step 02 | Click the social icons, Consult on WhatsApp, Account and Bag
[5 empty] | Step 03 | Click the logo from inner pages
[5 empty] | Step 04 | Scroll and watch the sticky header and the top announcement bar
TC_BW_NAV_002 | Added | Navigation | Verify mobile hamburger menu | Mobile | Step 01 | Open the menu | Android and iPhone | Menu fits the screen, opens and closes cleanly and does not lock the page |  | High | Pass | Navigation | Mobile
[5 empty] | Step 02 | Tap each item
[5 empty] | Step 03 | Close via X and outside tap
TC_BW_NAV_003 | Added | Navigation | Verify every footer and social link | Footer visible | Step 01 | Click every footer link: Botanical Store, The ritual, Our story, Questions & FAQ, Track Order, Store Admin & Catalog, Customer Account & Orders, Privacy policy, Terms & conditions, Refunds & cancellations, Shipping, WhatsApp Concierge | All footer links | No broken links; correct destinations; phone, email, WhatsApp and social links open correctly |  | Medium | Pass | Navigation | Both
[5 empty] | Step 02 | Click every contact line and social link
[5 empty] | Step 03 | Check new tab behaviour
TC_BW_NAV_004 | Added | Navigation | Verify 404 page and invalid URLs | None | Step 01 | Open /does-not-exist | /products/invalid, /collection/invalid, /does-not-exist | Branded 404 with navigation; no server error text |  | Medium | Fail | Error Handling | Both
[5 empty] | Step 02 | Open /collection/invalid-product
[5 empty] | Step 03 | Use the home link on the 404
TC_BW_NAV_005 | Added | Navigation | Verify browser Back, Forward and Refresh through the whole flow | Item in bag | Step 01 | Go Home to Product to Bag to Checkout | Full flow | No broken state, lost bag or duplicate actions; form data behaviour is sensible |  | Medium | Pass | State and Session | Both
[5 empty] | Step 02 | Press Back and Forward at each step
[5 empty] | Step 03 | Refresh at each step
TC_BW_COLL_002 | Added | Collection page | Verify search edge cases | Collection page | Step 01 | Search empty | Listed inputs | Case-insensitive match; clean no-result message; special characters safe; clearing restores all products |  | Medium | Pass | Negative | Both
[5 empty] | Step 02 | Search 'ROSE', ' rose ', 'xyz', '<b>', '%', very long text
[5 empty] | Step 03 | Clear search
TC_BW_PDP_002 | Added | Product pages | Verify all 5 products: photos, description, usage, ingredients | Products live | Step 01 | Open Beetroot, Orange Peel, Rose Petal, Kaolin Clay and Moringa | Beetroot ₹399, Orange Peel ₹349, Rose Petal ₹499, Kaolin Clay ₹299, Moringa ₹379 (confirm at 100% zoom) | All content present, accurate and readable; no broken images; each product in the correct category |  | High | Pass | Content | Both
[5 empty] | Step 02 | For each check photos, description, usage directions, ingredients, price, MRP, size
TC_BW_PDP_003 | Added | Product pages | Verify product page URL, title, refresh and share | Product known | Step 01 | Open a product link directly in a new tab | Product URL | Direct and refreshed URLs load fully; title reads '<name> ¦ Bhumae Wellness' |  | Medium | Pass | SEO | Both
[5 empty] | Step 02 | Refresh
[5 empty] | Step 03 | Check the browser tab title
TC_BW_PDP_004 | Added | Product pages | Verify WhatsApp link behaviour on mobile and desktop | Product page | Step 01 | Click Consult on WhatsApp on mobile | Android, iPhone, desktop | Opens WhatsApp app or WhatsApp Web with the right number and a sensible message |  | Medium | Pass | Functional | Both
[5 empty] | Step 02 | Click it on desktop
[5 empty] | Step 03 | Check the pre-filled message and number
TC_BW_PDP_005 | Added | Product pages | Verify Reviews section behaviour | Product page | Step 01 | Scroll to Reviews | N/A | Shows 'No reviews yet'; any form validates input and works or is clearly absent |  | Low | Pass | Functional | Both
[5 empty] | Step 02 | Look for any review form or button
[5 empty] | Step 03 | Try submitting if present
TC_BW_BAG_003 | Added | Bag | Verify bag open and close methods across pages | Item in bag | Step 01 | Open bag from Home, Collection, Product and policy pages | All pages | Opens everywhere with identical contents; all close methods work; page behind does not scroll |  | High | Pass | Functional | Both
[5 empty] | Step 02 | Close with X, overlay click and Esc
TC_BW_BAG_004 | Added | Bag | Verify free-shipping threshold boundaries and progress bar | Know product prices | Step 01 | Build bags worth about ₹598, 599 and 600 | Kaolin x2 = ₹598 (shipping 49, 'Add ₹1 more'); Kaolin + Orange = ₹648 (free). For exactly ₹599 temporarily set a product price to 599 in admin (ADM_006) and restore | Shipping is free from ₹599 on subtotal; ₹49 below it; progress bar and message correct on each side; banner says FREE express shipping on ₹599+ |  | High | Pass | Boundary | Both
[5 empty] | Step 02 | Compare delivery charge and note at each
TC_BW_BAG_005 | Added | Bag | Verify bag persistence | Item in bag | Step 01 | Refresh | 1 to 2 items | Bag persists across refresh, tabs and restart; it is kept in the browser (local storage, per the Privacy policy) so it does not follow the customer to another device; after clearing data it is empty with no errors |  | Medium | Pass | State and Session | Both
[5 empty] | Step 02 | Open a new tab
[5 empty] | Step 03 | Close and reopen the browser
[5 empty] | Step 04 | Clear site data
TC_BW_BAG_006 | Added | Bag | Verify rapid clicks and double add | Product page | Step 01 | Double-click Add to Bag | N/A | Quantity matches intended actions; no duplicate lines, frozen bag or wrong totals |  | Medium | Pass | Negative | Both
[5 empty] | Step 02 | Rapidly click + and - in the bag
[5 empty] | Step 03 | Add and remove quickly
TC_BW_BAG_007 | Added | Bag | Verify the limit of 10 when adding repeatedly | Product page | Step 01 | Add the same product from the product page 11 times | Total 11 and 12 | Total per product never exceeds 10 and a clear message appears |  | Medium | Blocked | Boundary | Both
[5 empty] | Step 02 | Add 6 then 6 again
[5 empty] | Step 03 | Edit quantity in the bag
TC_BW_BAG_008 | Added | Bag | Verify bag updates when price or stock changes while in bag | Admin and storefront open | Step 01 | Add a product | Price change, stock 0 | Bag and checkout use current price; out-of-stock item is flagged or blocked; restore values afterwards |  | Medium | Pass | Data Integrity | Desktop
[5 empty] | Step 02 | In admin change its price or set stock 0
[5 empty] | Step 03 | Refresh the bag and open checkout
TC_BW_BAG_009 | Added | Bag | Verify bag in two tabs stays in sync | Two tabs | Step 01 | Add an item in tab 1 | 2 tabs | Bag state consistent after refocus or refresh; no ghost items |  | Low | Pass | State and Session | Desktop
[5 empty] | Step 02 | Switch to tab 2 and open the bag
[5 empty] | Step 03 | Remove in tab 2 and check tab 1
TC_BW_CHK_002 | Added | Checkout form | Verify field validation boundaries | On checkout | Step 01 | Test name: empty, 1 char, digits, symbols, 100+ chars | See steps | Invalid values rejected with clear messages; valid variants (+91, spaces) handled or explained; long text does not break layout |  | High | Fail | Validation | Both
[5 empty] | Step 02 | Test phone: 9 digits, 11 digits, +91, spaces, letters, starts with 0 to 5
[5 empty] | Step 03 | Test email variants
[5 empty] | Step 04 | Test address and PIN lengths
TC_BW_CHK_003 | Added | Checkout form | Verify PIN, city and state consistency | On checkout | Step 01 | Enter 110001 and 202002 in turn | PIN 110001 while State still shows the default Uttar Pradesh; PIN 202002; edit city and state after auto-fill | City and state follow the PIN or a mismatch is flagged; the state stored on the order is correct (needed for CGST+SGST vs IGST on the invoice) |  | High | Fail | Data Integrity | Both
[5 empty] | Step 02 | Edit the auto-filled city and state
[5 empty] | Step 03 | Enter a PIN then change it
TC_BW_CHK_004 | Added | Checkout form | Verify double submit, refresh and Back after placing an order | Valid checkout | Step 01 | Click Place Order twice quickly | 1 order | Only one order created; refresh does not reorder; Back does not resubmit |  | High | Pass | Negative | Both
[5 empty] | Step 02 | Refresh the confirmation page
[5 empty] | Step 03 | Press Back after confirmation
TC_BW_CHK_005 | Added | Checkout form | Verify order summary and totals on checkout | Items in bag | Step 01 | Compare the summary with the bag | 2 products | Items, quantities, discount, delivery and total match the bag |  | High | Pass | Data Integrity | Both
[5 empty] | Step 02 | Apply a discount
[5 empty] | Step 03 | Check delivery and total
TC_BW_CHK_006 | Added | Checkout form | Verify direct access to checkout with an empty bag | Empty bag | Step 01 | Open the checkout URL directly | Checkout URL | Redirects or shows empty-bag message; no blank order is possible |  | Medium | Pass | Negative | Both
[5 empty] | Step 02 | Try to place an order
TC_BW_CHK_007 | Added | Checkout form | Verify mobile keyboards, autofill and layout on checkout | Mobile | Step 01 | Tap phone and email fields | Android, iPhone | Numeric keypad for phone, email keyboard for email; button reachable; no zoom jump on iPhone |  | Medium | Pass | Usability | Mobile
[5 empty] | Step 02 | Use autofill
[5 empty] | Step 03 | Check the Place Order button with the keyboard open
TC_BW_CHK_008 | Added | Checkout form | Verify behaviour on slow or lost network | Valid checkout | Step 01 | Throttle to Slow 3G and place an order | Slow 3G, offline | Loading state shown; friendly error offline; no duplicate order on retry |  | Medium | Pass | Error Handling | Desktop
[5 empty] | Step 02 | Go offline and place an order
[5 empty] | Step 03 | Restore and retry
TC_BW_CHK_009 | Added | Checkout form | Verify script and SQL input in all fields | On checkout and Track Order | Step 01 | Enter <script>alert(1)</script> and ' OR 1=1 -- in name, address, track fields | Injection strings | No script runs on any page, admin or email; input stored safely or rejected |  | High | Fail | Security | Desktop
[5 empty] | Step 02 | Place the order and view admin and email
TC_BW_ORD_002 | Added | Order data | Verify one order shows identical data everywhere | Order placed | Step 01 | Compare confirmation page, email, store alert, tracking, admin and invoice | Own order | All values identical in every place; timestamps in IST |  | High | Pass | Data Integrity | Desktop
[5 empty] | Step 02 | Check items, total, address, phone, date
TC_BW_ORD_003 | Added | Order data | Verify stock reduces after an order | Note stock first | Step 01 | Note a product's stock | Qty 2 | Stock reduces by 2 and is restored on cancel (A5) |  | High | Pass | Data Integrity | Desktop
[5 empty] | Step 02 | Place a COD order for 2 units
[5 empty] | Step 03 | Check stock in admin and shop
TC_BW_ORD_004 | Added | Order data | Verify ordering more than available stock | Admin access | Step 01 | Set stock to 2 | Stock 2, qty 3 | Quantity limited or blocked with a clear message; stock never goes negative |  | High | Pass | Boundary | Both
[5 empty] | Step 02 | Add 3 to the bag and check out
[5 empty] | Step 03 | Restore stock
TC_BW_ORD_005 | Added | Order data | Verify order reference uniqueness and format | Two or more orders | Step 01 | Place two orders | BHU-... | References are unique, correctly formatted and sequential or random as designed |  | Low | Pass | Data Integrity | Desktop
[5 empty] | Step 02 | Compare references
TC_BW_DISC_002 | Added | Discount codes | Verify discount edge cases | Codes from ADM_010; code box is in the checkout order summary | Step 01 | Test lower case, extra spaces, same code twice, ₹699 vs ₹700 minimum | ₹100 off with ₹700 minimum: Beetroot + Kaolin = ₹698 (refused) vs Beetroot + Orange = ₹748 (applies); lower case, spaces, same code twice | Rules applied exactly; total never negative; shipping and COD fee are not discounted; behaviour of free shipping after the discount is consistent (see DISC_004) |  | High | Pass | Boundary | Both
[5 empty] | Step 02 | Check 10 percent rounding
[5 empty] | Step 03 | Refresh with code applied
TC_BW_DISC_003 | Added | Discount codes | Verify expired and paused codes at checkout | Codes from A10 | Step 01 | Apply the expired code | 3 codes | Each refused with a clear message |  | High | Pass | Negative | Both
[5 empty] | Step 02 | Apply the paused code
[5 empty] | Step 03 | Apply the deleted code
TC_BW_EML_003 | Added | Email | Verify email content, rendering and deliverability | Email received | Step 01 | Open on Gmail app and desktop | Name with apostrophe | Renders cleanly on mobile and desktop; links work; authentication results pass |  | High | Pass | Email | Both
[5 empty] | Step 02 | Check logo, layout, links, spelling and special characters in names
[5 empty] | Step 03 | View original headers for SPF, DKIM and DMARC
TC_BW_TRK_003 | Added | Order tracking | Verify tracking negative cases and privacy | Order exists | Step 01 | Enter invalid, lower case, spaced and another order's reference | Real format BHU-YYYYMMDD-XXXXXX (6-character suffix) versus the placeholder BHU-YYYYMMDD-XXXXXX (4 characters); lower case, spaces, wrong date; mobile 9 digits, 11 digits, +91 prefix, letters; mobile with no orders | Friendly 'not found' or validation message; one field accepts either a reference or a 10-digit mobile; no data of other customers exposed; no full address or phone shown |  | High | Pass | Security | Both
[5 empty] | Step 02 | Enter a mobile with no orders
[5 empty] | Step 03 | Try adjacent reference numbers
TC_BW_TRK_004 | Added | Order tracking | Verify tracking status follows admin status | Order exists | Step 01 | Change Manual Status in admin | Statuses available | Tracking status matches admin status each time |  | Medium | Pass | Integration | Desktop
[5 empty] | Step 02 | Check Track Order after each change
TC_BW_POL_002 | Added | Policy and contact | Verify policy content matches site behaviour | Policy pages open | Step 01 | Compare Terms statements with the site (prices GST-inclusive, shipping and COD fee shown at checkout, contract formed when dispatch is confirmed, 18+ rule, full refund on cancelled paid orders) | Privacy, Terms, Shipping, Refunds | No contradictions between policies, checkout, emails and admin behaviour; contact details identical everywhere; no placeholder text |  | Medium | Pass | Content | Both
[5 empty] | Step 02 | Compare Shipping and Refunds pages with PIN checker, ₹599 free shipping and COD limit
[5 empty] | Step 03 | Check Privacy statements (bag kept in browser, no card data stored, grievance officer details)
[5 empty] | Step 04 | Check 'Last updated 11 September 2026' on Privacy and Terms
TC_BW_ADM_012 | Added | Admin security | Verify admin access control and session | Signed out | Step 01 | Open admin order, invoice and product URLs while signed out | Admin URLs | Signed-out access redirects to sign-in; no data after Back; lockout or delay on repeated failures; password never shown |  | High | Fail | Security | Desktop
[5 empty] | Step 02 | Sign out then press Back
[5 empty] | Step 03 | Leave the session idle
[5 empty] | Step 04 | Try several wrong passwords
TC_BW_ADM_013 | Added | Admin products | Verify product form validation | Admin access | Step 01 | Save with empty name | Invalid values | Clear validation errors; no invalid product saved; storefront stays clean |  | High | Fail | Validation | Desktop
[5 empty] | Step 02 | Enter negative, decimal and huge price and stock
[5 empty] | Step 03 | Set price above MRP
[5 empty] | Step 04 | Use special characters and a 500 character description
TC_BW_ADM_014 | Added | Admin products | Verify image upload types and sizes | Image files ready | Step 01 | Upload JPG, PNG, WebP and iPhone HEIC | Various files | Supported types work and are not stretched; unsupported types are rejected with a message |  | Medium | Pass | Validation | Desktop
[5 empty] | Step 02 | Upload a PDF and a 10 MB image
[5 empty] | Step 03 | Use a filename with spaces and symbols
TC_BW_ADM_015 | Added | Admin products | Verify deleting a product that is in a bag or past order | Admin access | Step 01 | Add a product to a bag | Test product | Bag handles the missing item; past orders still show the product details |  | Medium | Pass | Data Integrity | Desktop
[5 empty] | Step 02 | Delete it in admin
[5 empty] | Step 03 | Refresh the bag and check old orders
TC_BW_ADM_016 | Added | Admin products | Verify editing name, description and category | Admin access | Step 01 | Edit name, description and category | Test product | Changes appear after refresh in the right tab; restored cleanly |  | Medium | Pass | Admin | Desktop
[5 empty] | Step 02 | Check the shop and category tabs
[5 empty] | Step 03 | Restore
TC_BW_ADM_017 | Added | Admin invoice | Verify invoice calculations | Orders from A3 | Step 01 | Recalculate taxable value and CGST, SGST or IGST by hand | Aligarh and Delhi orders | All amounts correct to 2 decimals; invoice numbers unique and sequential |  | High | Pass | Data Integrity | Desktop
[5 empty] | Step 02 | Check rounding, total, invoice number sequence and date
TC_BW_ADM_018 | Added | Admin orders | Verify orders list with many orders and status changes | Several orders | Step 01 | Check sorting, search or filter if present | 3+ orders | List accurate and readable; status changes saved; no wrong transitions |  | Medium | Pass | Admin | Desktop
[5 empty] | Step 02 | Change status through each option
[5 empty] | Step 03 | Check list after cancel
TC_BW_UI_001 | Added | Responsive | Verify layout at key widths and orientations | DevTools | Step 01 | Test 320, 375, 414, 768, 1024, 1440, 1920 px | Widths listed | No clipped or overlapping content or sideways scroll; touch targets at least 44px |  | High | Fail | Responsive | Both
[5 empty] | Step 02 | Rotate mobile to landscape
TC_BW_UI_002 | Added | Visual | Verify images, alignment and the empty areas beside the carousel | Home page at 100% zoom | Step 01 | Scroll every page and check images | 1440 and 1920 px | No broken or blurry images; no overlap; carousel side areas look intentional |  | High | Pass | UI and Visual | Both
[5 empty] | Step 02 | Check text over images
[5 empty] | Step 03 | Check side areas of the carousel on wide screens
TC_BW_UI_003 | Added | Performance | Verify page speed and image weight | Chrome Lighthouse | Step 01 | Run Lighthouse mobile and desktop on Home, Collection, Product | 3 pages | Usable within about 3 seconds on 4G; no layout shift; heavy assets reported |  | Medium | N/A | Performance | Both
[5 empty] | Step 02 | Throttle to Slow 4G
[5 empty] | Step 03 | Note LCP, CLS and heavy images or video
TC_BW_UI_004 | Added | Accessibility | Verify keyboard, focus, contrast and labels | Desktop | Step 01 | Tab through the page and the bag | Keyboard only | Logical focus order; visible focus; labels present; contrast acceptable |  | Medium | Pass | Accessibility | Desktop
[5 empty] | Step 02 | Check focus is trapped in the open bag
[5 empty] | Step 03 | Check contrast on dark sections
[5 empty] | Step 04 | Check alt text and button labels
TC_BW_UI_005 | Added | Technical | Verify console errors and failed requests | DevTools | Step 01 | Load every page | All pages | No red errors, no 4xx or 5xx requests, no mixed content |  | Medium | Pass | Error Handling | Desktop
[5 empty] | Step 02 | Review Console and Network
[5 empty] | Step 03 | Check for mixed content
TC_BW_UI_006 | Added | Technical | Verify HTTPS, redirects and certificate | Browser | Step 01 | Open http:// and www versions | http and www URLs | Redirects to the single https URL; valid certificate |  | Medium | Pass | Security | Desktop
[5 empty] | Step 02 | Check the padlock
TC_BW_UI_007 | Added | SEO | Verify titles, meta tags, favicon, robots and sitemap | Browser | Step 01 | View page source meta title and description | All main pages | Unique titles and descriptions; favicon present; indexing settings match launch intent (confirm with client) |  | Low | Blocked | SEO | Desktop
[5 empty] | Step 02 | Check favicon and share preview
[5 empty] | Step 03 | Open /robots.txt and /sitemap.xml
TC_BW_UI_008 | Added | Compatibility | Verify Firefox and Edge | Browsers installed | Step 01 | Run Home, Product, Bag and Checkout | Firefox, Edge | Parity with Chrome |  | Medium | Pass | Compatibility | Desktop
[5 empty] | Step 02 | Compare with Chrome
TC_BW_UI_009 | Added | Compatibility | Verify third-party content failure (Instagram, fonts, WhatsApp) | DevTools or ad blocker | Step 01 | Block the Instagram embed and external fonts | Blocked requests | Page still renders; layout intact; sensible fallback |  | Low | Pass | Error Handling | Desktop
[5 empty] | Step 02 | Reload Home
TC_BW_EXP_001 | Added | Exploratory | Time-boxed exploratory session (60 minutes) per device | Charter ready | Step 01 | Test like a first-time customer on a phone | Free testing | No crashes or confusing behaviour; usability issues logged |  | Medium | Pass | Exploratory | Both
[5 empty] | Step 02 | Try odd orders: many items, long names, back and forth
[5 empty] | Step 03 | Note anything confusing
TC_BW_CHK_010 | Added | Checkout totals | Verify the COD fee of ₹30 across all places | Items in bag, COD selected | Step 01 | Check subtotal, shipping, COD fee and total in the checkout summary | Beetroot x1: 399+49+30=478. Beetroot + Orange Peel: 748+0+30=778 (matches the existing COD order in admin, so the fee applies even when shipping is free) | Total = subtotal - discount + shipping + COD fee; the fee applies only to COD; fee and total are identical everywhere; bag total (₹448) differing from checkout (₹478) is flagged for client confirmation (Terms say the fee is shown at checkout) |  | High | Pass | Data Integrity | Both
[5 empty] | Step 02 | Check the button amount
[5 empty] | Step 03 | Repeat with a bag of ₹599 or more and with a discount
[5 empty] | Step 04 | Compare with confirmation page, email, admin and invoice
TC_BW_BAG_010 | Added | Bag | Verify GST-inclusive amount and totals in the bag | Prices known | Step 01 | Add Beetroot and read 'Inclusive of ₹60.86 GST' | 399 x 18/118 = 60.86 | GST text matches the maths for every combination; confirm with client whether shipping and the COD fee are inside the GST figure |  | High | Pass | Data Integrity | Both
[5 empty] | Step 02 | Recalculate GST as price x 18/118
[5 empty] | Step 03 | Repeat for 2 and 3 products and for quantities
TC_BW_BAG_011 | Added | Bag | Verify the 'Pairs well with your ritual' suggestions | Item in bag | Step 01 | Click + ADD on a suggestion | Orange Peel 349, Rose Petal 499 | Suggestions exclude items already in the bag; + ADD adds one unit and updates totals; empty suggestion area handled cleanly |  | Medium | Pass | Functional | Both
[5 empty] | Step 02 | Check totals and progress bar
[5 empty] | Step 03 | Add every product so no suggestion remains
TC_BW_PDP_006 | Added | Product page | Verify tabs, ritual steps, patch test advice, embed and related products | Product page | Step 01 | Read the Ritual steps (Measure, Blend, Rinse) and Patch Test First advice | Beetroot page | Content complete and correct; embed plays; related cards link to the right products (not itself) and look finished |  | Medium | Pass | Functional | Both
[5 empty] | Step 02 | Open each tab
[5 empty] | Step 03 | Play the Instagram embed and click Open reel on Instagram
[5 empty] | Step 04 | Check the 'Pair with more from the collection' cards and View all
TC_BW_PDP_007 | Added | Product page | Verify Buy Now / Instant Checkout | Empty bag, then bag with items | Step 01 | Click Buy Now with quantity 1 and 3 | Beetroot | Goes straight to checkout with the right item and quantity; behaviour with existing bag items is consistent and totals correct |  | High | Fail | Functional | Both
[5 empty] | Step 02 | Repeat with items already in the bag
[5 empty] | Step 03 | Return from checkout
TC_BW_PDP_008 | Added | Product page | Verify stock text and the product page quantity selector | Admin access | Step 01 | Compare 'In Stock (24 units available)' with admin stock | Stock 24 | Displayed stock equals admin stock and updates after orders and cancellations; quantity limits respected |  | Medium | Pass | Data Integrity | Both
[5 empty] | Step 02 | Place or cancel an order and recheck
[5 empty] | Step 03 | Try quantity above stock and above 10
TC_BW_PDP_009 | Added | Product page | Verify safety and claim wording | Product pages | Step 01 | Check 'Formulated for external ritual use only. Not for ingestion.' and Patch Test advice on all 5 products | All 5 products. FAQ and Terms name only Beetroot Powder as external use only; confirm the wording for the other four | Safety text present on every product, correctly spelled and consistent with FAQ, Terms and pouch specifications |  | Medium | Pass | Content | Both
[5 empty] | Step 02 | Check claims (100% pure botanical, 100% net weight, vegan)
TC_BW_COLL_003 | Added | Collection page | Verify Sort products with tabs and search | Collection page | Step 01 | Select each Sort option | All sort options | List order is correct for each option; combinations work; no products lost or duplicated |  | Medium | Blocked | Functional | Both
[5 empty] | Step 02 | Combine sorting with a tab and a search
[5 empty] | Step 03 | Refresh and use Back
TC_BW_COLL_004 | Added | Collection page | Verify product card buttons and the concierge banner | Collection page | Step 01 | Click Add to bag on a card | 5 cards | Add to bag opens the bag with the right item; the second button and banner open their intended destination |  | Medium | Pass | Functional | Both
[5 empty] | Step 02 | Click the second button on each card
[5 empty] | Step 03 | Click the banner button 'Select any pure botanicals. Direct concierge consultations.'
TC_BW_PAY_003 | Added | Payment messaging | Verify payment claims match what is actually available | Online payment is 'Opening soon' | Step 01 | Read the top bar ('payment gateway & COD available'), footer ('Secure payment gateway gateway'), product page ('Secure Payment Gateway UPI, cards, netbanking, COD') and checkout ('Powered by payment gateway, zero payment surcharge') | All pages | Messages do not promise online payment before it works, or the client confirms the wording is accepted for launch |  | High | Pass | Content | Both
[5 empty] | Step 02 | Compare with the greyed online option
TC_BW_NAV_006 | Added | Navigation | Verify The Ritual and Our Story pages | None | Step 01 | Open /ritual: read 'A few quiet minutes', the 3 steps, the 4 cards (One ingredient, 100% pure, Prepared fresh, 100 g pouches) and click 'Explore the collection' | /ritual, /story | Both pages load fully; images, video and embed work; every button goes to the intended place; claims (100 g pouches, one ingredient) match the products |  | Medium | Pass | Functional | Both
[5 empty] | Step 02 | Open /story: read the sections, click 'Meet the collection'
[5 empty] | Step 03 | Play the 'A considered moment' video and the Instagram embed
[5 empty] | Step 04 | Click 'Visit Instagram' and 'Open reel on Instagram'
TC_BW_NAV_007 | Added | Navigation | Verify Questions & FAQ page | None | Step 01 | Open /questions | 4 FAQ items | Accordions work with mouse, touch and keyboard; answers agree with product pages and Terms (external use, patch test, storage); chevron state matches open or closed |  | Medium | Pass | Content | Both
[5 empty] | Step 02 | Expand and collapse each of the 4 questions (preparation, mask time, internal use, storing the pouch)
[5 empty] | Step 03 | Check whether one or many can stay open
[5 empty] | Step 04 | Read 'Follow the pouch. Prepare fresh.' text
TC_BW_NAV_008 | Added | Navigation | Verify Contact page channels and WhatsApp links | None | Step 01 | Open /contact | Contact page has no form | WhatsApp opens the right number with the pre-filled enquiry; social cards open the correct profiles in a new tab; phone and email links work; details match the footer, Terms and Privacy pages |  | Medium | Pass | Functional | Both
[5 empty] | Step 02 | Click the WhatsApp BHUMAE card and check the number and pre-filled text
[5 empty] | Step 03 | Click Instagram, Facebook and Pinterest cards
[5 empty] | Step 04 | Click Call us (tel:) and Email (mailto:)
[5 empty] | Step 05 | Click 'Read common questions' and 'Book a consultation'
TC_BW_SEC_001 | Added | Security | Verify the public 'Store Admin & Catalog' footer link | None | Step 01 | Click the link signed out | Footer link | Only sign-in is visible; no admin data exposed; client confirms the link is meant to be public |  | Medium | Pass | Security | Desktop
[5 empty] | Step 02 | Check the page shows only the sign-in screen
[5 empty] | Step 03 | Check /admin is not indexable (robots or noindex) and no data loads before sign-in
TC_BW_ADM_019 | Added | Admin products | Verify the inline stock stepper (-5, +5 and typed values) | Admin access; baseline stock Beetroot 24, Orange Peel 24, Rose 25, Kaolin 25, Moringa 25 (total 123) | Step 01 | Click +5 and -5 on a product | Beetroot 24 | Stock changes save once, show a confirmation or the new value after refresh, never go below 0, and the storefront text 'In Stock (N units available)' and Overview inventory total follow; status switches to out of stock at 0 |  | High | Pass | Admin | Desktop
[5 empty] | Step 02 | Type a value directly and leave the field
[5 empty] | Step 03 | Try to go below 0 and type a negative or non-numeric value
[5 empty] | Step 04 | Check the storefront and the Overview total after each change
[5 empty] | Step 05 | Restore the original stock
TC_BW_ADM_020 | Added | Admin overview | Verify Overview metrics | Admin access | Step 01 | Compare Total realized revenue, Total orders placed (and awaiting fulfilment), Active SKUs and Total inventory units with the Orders and Catalog tabs | Baseline: revenue 0, orders 2, SKUs 5, units 123 | Numbers match the data; revenue counts only paid and delivered orders; 'awaiting fulfilment' counts pending COD orders (currently 0 while one COD order is pending, confirm intent); category count is correct; date format is consistent |  | Medium | Pass | Data Integrity | Desktop
[5 empty] | Step 02 | Place and cancel an order and recheck
TC_BW_ADM_021 | Added | Admin payment settings | Verify Payment Gateway tab settings and their effect on the storefront | Admin access; change settings only in a quiet period and restore | Step 01 | Read the payment gateway panel (Test mode badge, key ID, mode choice, webhook URL) but do not enter keys | COD fee 30, max 5000 | COD fee and limit shown on the storefront follow the admin values; disabling COD blocks COD cleanly; status messages (test mode, 'live payments enabled', Opening soon on the storefront) are consistent; no secret is fully displayed |  | High | Blocked | Admin | Desktop
[5 empty] | Step 02 | Change COD handling fee to 40 and max order value to 4000, save, check checkout and the COD limit message, then restore 30 and 5000
[5 empty] | Step 03 | Untick COD enabled, check checkout, then restore
[5 empty] | Step 04 | Review the Direct UPI QR and VPA panel
TC_BW_ADM_022 | Added | Admin orders | Verify orders table content, formatting and actions by status | At least one COD and one cancelled order | Step 01 | Read each column (reference, date and time, customer, address, total, payment type, status) | Existing orders and your own | Text is spaced and wrapped properly (the screenshot shows name and 'Ph:' and address lines running together); actions match the status; reference format BHU-YYYYMMDD-XXXXXX; times shown in IST |  | Medium | Pass | UI and Visual | Desktop
[5 empty] | Step 02 | Check spacing between name and phone and between address lines
[5 empty] | Step 03 | Compare actions for PENDING_COD (Ship, Invoice, Resend emails, Manual status) with CANCELLED (Manual status only)
[5 empty] | Step 04 | Check newest-first order and long names or addresses
TC_BW_ADM_023 | Added | Admin catalog | Verify category chips and Add Catalog Category | Admin access | Step 01 | Compare each chip count with the products listed (Botanical Powders 2, Floral Edits 1, Clays & Minerals 1, Hair & Scalp Rituals 1, Wellness Sets & Combos 0) | New category 'QA Test' | Counts are correct; chip highlight is not confusing; a new category appears as a storefront tab only when it has products; empty categories stay hidden; cleanup leaves the catalog unchanged |  | Medium | Pass | Admin | Desktop
[5 empty] | Step 02 | Check 'All SKUs' and 'All Collection' chips and their highlight
[5 empty] | Step 03 | Add a test category, assign a product, check the storefront tab, then delete it
TC_BW_PIN_012 | Added | PIN code | Cross-check storefront PIN result against the admin courier partner PIN tester | Admin access; confirm with the developer that Check PIN is read-only | Step 01 | Enter each PIN in the admin Live Pincode Serviceability Tester | 110001, 560001, 400001, 202002, 700001, 600001, 744101, 999999 | Storefront and admin agree on serviceable, not served and invalid for every PIN; do not click Ship via courier partner |  | High | Fail | Integration | Desktop
[5 empty] | Step 02 | Enter the same PIN on the storefront checkout
[5 empty] | Step 03 | Compare the results
TC_BW_SEC_002 | Added | Security and privacy | Verify privacy claims against actual behaviour | DevTools Network tab open | Step 01 | Add items to the bag and watch for server calls before checkout | Privacy policy | Bag data stays in the browser until checkout; no card data handled by the site; third-party content is limited to the Instagram embed and the policy wording is acceptable to the client |  | Medium | Blocked | Security | Desktop
[5 empty] | Step 02 | Place a COD order and confirm no card or UPI data is requested or stored
[5 empty] | Step 03 | Load a page with the Instagram embed and note third-party requests and cookies
[5 empty] | Step 04 | Compare with the Privacy policy text
TC_BW_DISC_004 | Added | Discount codes | Verify discount maths with shipping, COD fee, GST and documents | Codes from ADM_010 | Step 01 | Apply a 10% code to Beetroot + Orange (748) | 748 less 10% = 673.20, shipping 0, COD fee 30, total 703.20 (confirm rounding) | Discount comes off products only; whether free shipping uses the total before or after the discount is consistent and agreed; GST on the invoice is calculated on the discounted value; the code used is visible in admin and documents |  | High | Pass | Data Integrity | Both
[5 empty] | Step 02 | Apply a code that drops the products total below ₹599
[5 empty] | Step 03 | Check shipping, COD fee and total
[5 empty] | Step 04 | Place a COD order and compare confirmation, email, admin and invoice
TC_BW_ADM_025 | Added | Admin video and reels | Verify the Video & Reels tab management | Admin access; restore anything changed | Step 01 | Open Video Testimonials (0) and click Add Video Testimonial: check the form and validation without saving junk | Valid reel link, 'abc', a YouTube link | Invalid links are rejected clearly; valid ones appear on the storefront after refresh; counts and cards update; empty-state text is correct; the reel stays on Home, Our Story and product pages as designed |  | Medium | Blocked | Admin | Desktop
[5 empty] | Step 02 | Open Instagram Reels (1): add, edit and remove a reel using valid, invalid and non-Instagram links
[5 empty] | Step 03 | Compare the four cards with the storefront
TC_BW_ADM_026 | Added | Admin discounts | Verify the Create a discount code form validation | Admin access | Step 01 | Submit with Code blank | WELCOME10, welcome10, 0, 101, -5 | Required fields enforced with clear messages; duplicates blocked; percent limited to a sensible range; minimum order optional; today's date means valid through today (IST); no broken or negative discounts can be saved |  | High | Pass | Validation | Desktop
[5 empty] | Step 02 | Use a duplicate code in a different case
[5 empty] | Step 03 | Enter Percent off as 0, 100, 101, -5, 10.5 and text
[5 empty] | Step 04 | Enter a negative or text Minimum order
[5 empty] | Step 05 | Pick a past and today's date as Last day valid
[5 empty] | Step 06 | Switch Type to the other option and repeat

## Regression
Regression Id | Linked Test Case Id | Scenario | Test Case | Client Check | Run 1 Status | Run 2 Status | Remarks
RG_001 | TC_BW_HOME_001 | Home page | Verify home page, product carousel and links | S1 | Pass
RG_002 | TC_BW_COLL_001 | Collection page | Verify category tabs and search | S2 | Blocked
RG_003 | TC_BW_PDP_001 | Product page | Verify product page photos, price, reviews and WhatsApp | S3 | Pass
RG_004 | TC_BW_BAG_001 | Bag | Verify bag add, quantity change, remove and free-delivery note | S4 | Pass
RG_005 | TC_BW_BAG_002 | Bag | Verify quantity limit of 10 | S5 | Pass
RG_006 | TC_BW_CHK_001 | Checkout form | Verify empty and invalid checkout fields | S6 | Pass
RG_007 | TC_BW_PIN_001 | PIN code | Verify deliverable PIN 202002 | S7 | Pass
RG_008 | TC_BW_PIN_002 | PIN code | Verify non-served PIN 744101 blocks order | S8 | Pass
RG_009 | TC_BW_PIN_003 | PIN code | Verify non-real PIN 999999 blocks order | S9 | Pass
RG_010 | TC_BW_PAY_001 | Payment | Verify payment options display | S10 | Pass
RG_011 | TC_BW_ORD_001 | Order | Place a Cash on Delivery order end to end | S11 | Pass
RG_012 | TC_BW_DISC_001 | Discount codes | Verify discount codes apply, fail and remove (after A10) | S12 | Pass
RG_013 | TC_BW_PAY_002 | Payment | Verify COD limit above ₹5,000 | S13 | Pass
RG_014 | TC_BW_STK_001 | Stock | Verify out of stock display | S14 | Pass
RG_015 | TC_BW_EML_001 | Email | Verify order confirmation email | T1 | Pass
RG_016 | TC_BW_EML_002 | Email | Verify store alert email | T2 | Pass
RG_017 | TC_BW_TRK_001 | Order tracking | Verify tracking by order reference | T3 | Pass
RG_018 | TC_BW_TRK_002 | Order tracking | Verify tracking by mobile number | T4 | Pass
RG_019 | TC_BW_POL_001 | Policy and contact | Verify policy and contact pages | T6 | Pass
RG_020 | TC_BW_ADM_001 | Admin login | Verify sign in and sign out | A1 | Pass
RG_021 | TC_BW_ADM_002 | Admin orders | Verify orders list | A2 | Pass
RG_022 | TC_BW_ADM_003 | Admin invoice | Verify tax invoice (Aligarh and Delhi) | A3 | Pass
RG_023 | TC_BW_ADM_005 | Admin order status | Verify cancelling an order restores stock | A5 | Pass
RG_024 | TC_BW_ADM_006 | Admin products | Verify editing price, MRP and stock | A6 | Pass
RG_025 | TC_BW_ADM_007 | Admin products | Verify adding a product with photos | A7 | Pass
RG_026 | TC_BW_ADM_010 | Admin discounts | Verify discount code management (run before S12) | A10 | Pass
RG_027 | TC_BW_DEV_001 | Device: Android | Run S1 to S11 on Android Chrome | D1 | Fail
RG_028 | TC_BW_DEV_002 | Device: iPhone | Run S1 to S11 on iPhone Safari | D2 | Pass
RG_029 | TC_BW_DEV_003 | Device: Desktop | Run S1 to S11 and A1 to A11 on desktop Chrome or Edge | D3 | Pass
RG_030 | TC_BW_HOME_002 | Home page | Verify hero, trust strip, section CTAs and the video | Added | Pass
RG_031 | TC_BW_NAV_001 | Navigation | Verify header menu, logo and sticky behaviour | Added | Pass |  | Logo wasn't visible in Desktop mode on mobile in some widths in Run 1
RG_032 | TC_BW_NAV_002 | Navigation | Verify mobile hamburger menu | Added | Pass
RG_033 | TC_BW_PDP_002 | Product pages | Verify all 5 products: photos, description, usage, ingredients | Added | Pass
RG_034 | TC_BW_BAG_003 | Bag | Verify bag open and close methods across pages | Added | Pass
RG_035 | TC_BW_BAG_004 | Bag | Verify free-shipping threshold boundaries and progress bar | Added | Pass
RG_036 | TC_BW_CHK_002 | Checkout form | Verify field validation boundaries | Added | Fail
RG_037 | TC_BW_CHK_003 | Checkout form | Verify PIN, city and state consistency | Added | Fail
RG_038 | TC_BW_CHK_004 | Checkout form | Verify double submit, refresh and Back after placing an order | Added | Pass
RG_039 | TC_BW_CHK_005 | Checkout form | Verify order summary and totals on checkout | Added | Pass
RG_040 | TC_BW_CHK_009 | Checkout form | Verify script and SQL input in all fields | Added | Fail
RG_041 | TC_BW_ORD_002 | Order data | Verify one order shows identical data everywhere | Added | Pass
RG_042 | TC_BW_ORD_003 | Order data | Verify stock reduces after an order | Added | Pass
RG_043 | TC_BW_ORD_004 | Order data | Verify ordering more than available stock | Added | Pass
RG_044 | TC_BW_DISC_002 | Discount codes | Verify discount edge cases | Added | Pass
RG_045 | TC_BW_DISC_003 | Discount codes | Verify expired and paused codes at checkout | Added | Pass
RG_046 | TC_BW_EML_003 | Email | Verify email content, rendering and deliverability | Added | Pass
RG_047 | TC_BW_TRK_003 | Order tracking | Verify tracking negative cases and privacy | Added | Pass
RG_048 | TC_BW_ADM_012 | Admin security | Verify admin access control and session | Added | Fail
RG_049 | TC_BW_ADM_013 | Admin products | Verify product form validation | Added | Fail
RG_050 | TC_BW_ADM_017 | Admin invoice | Verify invoice calculations | Added | Pass
RG_051 | TC_BW_UI_001 | Responsive | Verify layout at key widths and orientations | Added | Fail
RG_052 | TC_BW_UI_002 | Visual | Verify images, alignment and the empty areas beside the carousel | Added | Pass
RG_053 | TC_BW_CHK_010 | Checkout totals | Verify the COD fee of ₹30 across all places | Added | Pass
RG_054 | TC_BW_BAG_010 | Bag | Verify GST-inclusive amount and totals in the bag | Added | Pass
RG_055 | TC_BW_PDP_007 | Product page | Verify Buy Now / Instant Checkout | Added | Fail
RG_056 | TC_BW_PAY_003 | Payment messaging | Verify payment claims match what is actually available | Added | Pass
RG_057 | TC_BW_ADM_019 | Admin products | Verify the inline stock stepper (-5, +5 and typed values) | Added | Pass
RG_058 | TC_BW_ADM_021 | Admin payment settings | Verify Payment Gateway tab settings and their effect on the storefront | Added | Blocked
RG_059 | TC_BW_PIN_012 | PIN code | Cross-check storefront PIN result against the admin courier partner PIN tester | Added | Fail
RG_060 | TC_BW_DISC_004 | Discount codes | Verify discount maths with shipping, COD fee, GST and documents | Added | Pass
RG_061 | TC_BW_ADM_026 | Admin discounts | Verify the Create a discount code form validation | Added | Pass